## Sheet1
Stage : Prototype 1 development, Duration : 5 weeks
Week No. | Date | Product Management (Lalith) | Firmware (Lalith) | Hardware (Sumit & Venketesh) | Product Design (Prithu)
Week 1 | 2025-08-25 | - Compile Product Requirement Document & get approved by client. - Compile (this) Project Planning Document & get it approved by client. - Every Monday & Thursday, Track and ensure that all tasks are moving on track, raise concerns if anything is lagging. - Every Monday & Thursday, Update the client on the project's progress. | - Understand the complete device specs - Plan Project timeline - Finalise hardware - Gather necessary resources for firmware development | - Plan Project Timeline, - Prepare Electronics Requirement Document - Prepare Hardware Architecture, Identification of parts and modules - Order/Procurement for Preliminary Prototype | - Review the Opensource STEP Files of ESP-ROLL - Order 3D print 1 set for trial assembly & reference. - Order remaining components
Week 2 | 2025-09-01 | - Every Monday & Thursday, Track and ensure that all tasks are moving on track, raise concerns if anything is lagging. - Every Monday & Thursday, Update the client on the project's progress. | - Make the DF-ROBOT OPEN-AI QA Firmware work - Flash the ESP-ROLL firmware onto the breadboard circuit and test its functionality. - Create a plan to integrate both the firmwares. - Start to integrate both the firmwares based on the plan. | - Receiving of components - Assembly of 2 Sets for Functional Testing and Firmware Development - Start of Schematic Design | - Assemble & Study 1 set of 3D printed ESP-ROLL - Order components for 10 prototypes (Part 1)
Week 3 | 2025-09-08 | - Every Monday & Thursday, Track and ensure that all tasks are moving on track, raise concerns if anything is lagging. - Every Monday & Thursday, Update the client on the project's progress. | - Complete Integration of both the firmwares and test the system. - Add firmware to fetch data and print it to the console log from the additional sensor modules. | - Completion of Schematic Design - BoM Generation - Components ordering for 10-15 Units - Start of PCB Layout | - Design PCB Layout - Design Magnetic attachment for the head.
Week 4 | 2025-09-15 | - Every Monday & Thursday, Track and ensure that all tasks are moving on track, raise concerns if anything is lagging. - Every Monday & Thursday, Update the client on the project's progress. | - Write down test cases and start testing the firmware on custom PCBs | - Completion of PCB Layout - Manufacturing Files Generation and PCB order placement | - Order components for 10 prototypes (Part 2)
Week 5 | 2025-09-22 | - Assemble all the 10 protoypes along with the rest of the team - Testing all the 10 units and ensure they are all working fine - Every Monday & Thursday, Track and ensure that all tasks are moving on track, raise concerns if anything is lagging. - Every Monday & Thursday, Update the client on the project's progress. | - Complete Product test and make it ready for delivery | - Receiving of components and PCBs - Assembly of 1st PCB and functional testing by flasing firmware - Assembly of All remaining PCBs and testing and handover for Mechanical Assembly - Complete Product test and make it ready for delivery | Complete Product test and make it ready for delivery | Note: This is a rough plan and changes can be made as per individual team's plan.